Click HERE to see the LEM request submission in Workfront.

After Request is submitted by the LEM in Workfront.

- Project Coordinator (PC) will convert the request into the required number of projects, depending on the requirements, which are Production, Translation, and Creation projects.

  - Click HERE for the guidance on creating Production Project

  - Click HERE for the guidance on creating Translation Project

Post Project/s Creation in Workfront, PC will

- Triage

Managed by: Project Coordinator (PC)

After a request is submitted by the LEM in Workfront, the PC converts it into the required number of projects (Production, Translation, and/or Creative). Once projects are created, the Triage process begins.

- Review the requirements and expected deliverables.

- Double-check all date fields (start, due dates, dependencies).

- Ensure all necessary attachments (briefs, brand guidelines, references) are uploaded.

- Follow the Triage Checklist to avoid missing critical inputs.

## 1.1	Handling Triage Failure

- PC Identifies Missing Information

  - Examples:

    - Creative brief missing.

    - File corrupted or encrypted.

    - Intake form incomplete (e.g., no due date, missing deliverable details).

- PC Raises an Issue Task

  - Create an Issue Task with Issue Type: Pending Clarification.

  - Assign the Issue to the LEM/Requester.

  - Document the specific missing details in the Issue description and comments.

  - Tag the LEM in the comment for visibility.

  - (PC and LEM can also connect on Chat/Call for a discussion, if needed)

- Update Project and Task Status

  - Set the Project Status from Planning ➝ Pending Clarification.

  - Set the Issue task status to In-Progress

  - Add a brief note in the Project comments (e.g., “Project moved to Pending Clarification — awaiting correct creative brief from LEM.”).

- LEM Provides Clarification

  - Once the LEM responds with the requested files or details, the PC:

    - Assigns the Issue to themselves for verification.

    - Reviews the submitted clarifications against project requirements.

- Verification & Closure

  - If the clarification resolves all issues:

    - Update the Issue task status from In Progress ➝ Closed.

    - Update the Project Status from Pending Clarification ➝ Current.

  - If clarification is still incomplete:

    - Add detailed comments explaining what is still missing.

    - Re-assign the Issue back to the LEM.

    - Keep the Project Status in Pending Clarification until resolved.

1.2	After completing the Triage checks (When Triage is PASS), the PC must:

- Assign the Asset Audit Task to the appropriate Channel Lead (CL).

- Add relevant comments/instructions in the Asset Audit Task for clarity.

- Ensure the CL is tagged in comments, so visibility is maintained.

- Update the Project Status:

  - From Planning ➝ Pre-Audit (if Pre-Audit is required)

  - From Planning ➝ Current (if no Pre-Audit is required)

1.3	Edge Case Scenario:

When Pre-Audit needs to be done on LEM’s request, even though the Production project has a dependency on Creative OR Translation project:

- PC will tag the (Channel Lead) CL in the comments, with the required information.

  - Tagging is mandatory as no task assignment is done for the CL

- PC will update the Status of the Project from Planning to Pre-Audit

- CL will pick the project and start with the Pre-Audit of the Production Project

- When the Pre-audit is complete, CL will

  - Update comments with relevant notes and requirements

  - Tag PC (mandatory as no task assignment is done for the CL)

  - Update the Status of the Project from Pre-Audit to Pre-Audit Complete

- In case, CL has commented with additional information/requirements, PC will

  - update the status of the Project from Pre-Audit to Planning

  - reach out to LEM for the additional information/requirements

  - PC will keep the project status as “Pending Clarification”, till the time LEM responds to PC with clarifications

  - PC will tag the CL again, and update Project Status from Planning/Pending Clarification to Pre-Audit, when the information/clarity is received from the LEM

Notes:

- This circle of Pre-Audit will continue till the time CL confirms that provided information is good to proceed with the Production project, once the Dependent project is completed.

- The project will finally be in the “Pre-Audit complete” status, till the time Dependent project is completed.

1.4	Best Practices for Triage:

      - Follow the Triage Checklist diligently to ensure no fields or attachments are missed.

      - Always tag the CL in comments, especially in Pre-Audit scenarios, to avoid delays.

      - Do not proceed without complete attachments; escalate missing items to the LEM immediately.

      - Use saved filters or dashboards (e.g., “Projects in Planning,” “Pending Pre-Audit”) for daily monitoring.

      - Batch triage similar request types (e.g., translations) to optimize efficiency while highlighting priority projects individually.

      - Be proactive with the LEM: flag potential delays or unclear inputs early instead of waiting for CL feedback.

- Asset Audit:

Managed by: Channel Lead (CL)

Asset Audit is a crucial quality checkpoint where the CL verifies that the project is ready to move into production. It ensures that the inputs received meet the required standards and that there are no gaps that could cause rework/blocker during execution.

2.1 When Asset Audit task is picked up, CL will

- Update the Asset Audit task status from New to In-Progress (SLA Starts HERE)

- Update the Project Status from Current to Audit Ongoing (happens automatically with automation)

- Perform the asset audit of the project (as stated below)

  - Review the intake form, creative briefs, and attachments for accuracy and completeness.

  - Validate that all requirements are clearly defined (deliverables, formats, languages, sizes, etc.).

  - Check dates and ensure they are realistic and in line with project dependencies.

  - Document findings, clarifications, or risks in the task comments for transparency.

  - Apply channel best practices and follow the Asset Audit Checklist.

  - Partial Readiness:
If some assets are ready but others are pending, CL may recommend moving approved parts forward while awaiting remaining inputs. Document this clearly in comments and tag PC.

  - Conflicting Inputs:
If the brief and attachments contradict each other (e.g., one file specifies banner size as 300x250, another as 320x250), CL must flag the discrepancy in comments and tag both PC and LEM.

  - Recurring Audit Failures:
If the same LEM submissions repeatedly fail audits, CL should document a summary of recurring issues and share with PC for escalation.

2.2 If Asset Audit FAILS, CL will (for Asset Audit Pass Goto 2.3)

- Create an Issue Task with Issue Type: Pending Clarification.

- Update comments with additional requirements, missing information, etc.

  - Tag PC

- Update the Project status from Audit Ongoing to Pending Clarification

- In case execution work cannot be started, because of missing or unclear information, CLs should update the (BIA) “Brief Input Accuracy” field at the request level “No”, and if the execution can be started, the BIA field should be marked as “Yes”.

- Assign the Issue to the PC.

- Document the specific missing details in the Issue description and comments.

- Tag the PC in the comments for visibility.

- (PC and LEM can also connect on Chat/Call for a discussion, if needed)

- Update Project and Task Status

  - Make sure that the Project Status is set to “Pending Clarification”. (happens automatically with automation)

  - Set the Issue task status to "Awaiting feedback”

  - Add a brief note in the Project comments

- LEM Provides Clarification, PC will

  - Once the LEM responds with the requested files or details, the PC:

    - Reviews the submitted clarifications against project requirements.

    - Tag CL to review the response/clarification from the LEM

    - Change the issue task status from Awaiting Feedback to In-Progress and change project status from Pending Clarification to Current

- Verification & Closure, CL will

  - If the clarification resolves all issues:

    - Update the Issue task status from In Progress ➝ Closed.

    - Update the Project Status from Current ➝ Audit Ongoing.

  - If clarification is still incomplete:

    - Add detailed comments explaining what is still missing.

    - Update the issue status as “Awaiting Feedback”

    - Re-assign the Issue back to the PC.

Keep the Project Status in Pending Clarification until resolved.

This circle of asset Audit will continue till the time CL confirms that provided information is good to proceed with the Development of Production project.

2.3 If Asset Audit PASSES, CL will

- Update the Asset Audit task status from In-Progress to Complete

- Check if Extraction is needed before the development can begin

- If Extraction is needed,

  - Provide details, references, instructions in the Asset extraction task

  - Assign the Asset Extraction task to Graphic Designer (GD), if required

  - Provide details, references, instructions in the Build task

  - Assign the Build task to Web Developer (WD)

  - Update Project status from Audit Ongoing to Awaiting Execution (happens automatically with automation)

  - Goto 3

- If Extraction is NOT needed, Goto 4

## 2.4	Best Practices for Asset Audit

- Follow the Asset Audit Checklist for every project without exception.

- Document required/provided clarifications in comments at the task level for easy reference by PC and LEM.

- Be specific in audit feedback — avoid generic comments like “missing details”; specify what is missing.

- Always tag PC when additional requirements are identified, to ensure they coordinate with the LEM.

- Avoid moving a project forward prematurely — unclear inputs almost always lead to delays later.

- Where possible, suggest solutions instead of only flagging issues (e.g., “Image size missing — recommend using last campaign’s 300x250 creative as a placeholder until confirmation”).

- For large projects with multiple assets, summarize the audit findings in a structured list to help PC and LEM resolve faster.

Production begins

Ideally, Development (Build) will start after the extraction task is complete. However, if the Build can start, while the extraction task is being worked upon, CLs should coordinate and decide for both tasks to be executed in parallel. Use Comments in Workfront to keep everyone informed.

3.	Asset Extraction

Managed by: Graphic Designer (GD), with oversight from the Channel Lead (CL)

Asset Extraction ensures that all creative materials are properly prepared, localized (if needed), and QA-verified before moving into the Build stage. It bridges the gap between raw creative assets and production-ready materials.

  - When Asset Extraction starts, GD will,

  - Update Asset Extraction task status from New to In-Progress

  - Update Project Status from Awaiting Execution – Execution In-Progress

  - Complete the required extraction activity and update relevant files, output and notes in Comments on the Asset Extraction task

    - Start the Asset Extraction task once assigned, updating its status accordingly.

    - Extract, adapt, or localize assets as per project requirements.

    - Ensure final outputs are in the correct formats, resolutions, and aligned with brand guidelines.

    - Add notes, references, and outputs in Workfront task comments for transparency.

- Parallel Execution with Build:
If the CL approves, Build may start while Extraction QA is ongoing. In such cases, GD must ensure preliminary assets are marked as Draft Safe, and any changes from QA are communicated to WD immediately.

- Localization Projects:
For multi-market localization, GD should create a versioning plan (e.g., naming convention with market codes) to avoid confusion.

- Capacity Constraints:
If no second GD is available for QA, CL must step in to either:

    - Perform the QA themselves, or

    - Adjust timelines so QA is not skipped.

## 3.2	Best Practices for Asset Extraction

- Follow the Checklist every time to ensure consistency in formats, resolutions, and compliance.

- Maintain editable source files in case further revisions are needed later.

- Document assumptions clearly in comments (e.g., “Using placeholder banner until final copy is received”).

- Communicate early if any extracted asset doesn’t meet expected quality (e.g., low-resolution originals).

- QA proactively before GD-QA review to reduce back-and-forth cycles.

- For multi-asset projects, create a quick summary list in comments with status for each asset (e.g., “5 banners extracted, 2 pending legal copy”)

  - When Asset Extraction is Complete, GD will,

  - Assign the Asset Extraction task to another GD resource for QA (consult with Channel lead, if needed)

  - Update Asset Extraction task status from In-Progress to Assigned to QA

    - QC of Asset Extraction can be skipped ONLY if it is a pure image extraction, however for any additional job, such as, new/scratch builds, update of existing images, combining images or localization, QA must be done.

  - When the Asset Extraction task is assigned to GD-QA, GD-QA will,

- Update Asset Extraction task status from Assigned to QA to QA In-Progress

  - Complete the QA of output basis output requirements, checklist, and best practices

- Technical Accuracy: Resolution, dimensions, formats, naming conventions.

- Brand Compliance: Fonts, logos, colors, and overall design alignment with brand guidelines.

- Content Accuracy: Correct copy, spelling, market-specific localization accuracy.

  - Add relevant notes in the comments of the Asset Extraction task

  - Summarize findings clearly and concisely for visibility.

  - Use a structured approach such as:

  - Pass/Fail status

  - Findings summary

  - Next action required

  - Example comment structure:

  - If issues are found, be specific:

  - “Banner for FR market has text cutoff on 300x250 creative. Please re-export with adjusted layout.”

  - Tag the original GD and CL in comments if corrections are needed

- Use the Asset Extraction QA Checklist to guide the review process.

- Cross-verify assets against the original brief and intake details provided by the LEM

  - If Asset Extraction Quality Check/Review FAILS, GD-QA Resource will, (for Asset Extraction Quality Review PASS Goto 3.5)

  - Add relevant notes, findings, details of QA Fail, in the comments of the Asset Extraction task

- Provide specific and actionable feedback, not generic remarks.

- Use a clear structure such as:

- Issue: Describe what went wrong

- Location/Asset: Specify which file or creative is affected.

- Required Fix: Detail exactly what needs to be done.

- Tag both the original GD and the CL in the comments to ensure visibility.

  - Assign the Asset Extraction task to the same GD, who initially worked on the Asset Extraction ticket.

  - This ensures continuity since the original GD is already familiar with the context and requirements.

  - If the original GD is unavailable:

  - The Channel Lead (CL) is responsible for re-assigning to another GD.

  - The CL must ensure the new GD has full access to prior files, notes, and QA feedback.

  - Update the status of the Asset Extraction task from QA In-Progress to New

  - Ensure the PC is informed (via tagging) if QA issues may affect the project timeline.

  - Goto 3.1

This circle of Asset Extraction and it’s review will continue till the time GD-QA confirms that provided information is good to proceed with the Development of Production project.

  - If Asset Extraction PASSES, GD-QA Resource will,

  - Add relevant notes, findings, assets, in the comments of the Build task

  - Document a summary of the QA review confirming the assets are ready for Build.

  - Use a structured comment format for clarity:

  - QA Result: PASS

  - Notes: All banners extracted successfully in required sizes and formats. Fonts and colors match brand guidelines.

  - Assets Ready: 5 banners, 2 hero images, 1 video thumbnail.

  - Additional Info: Localization checked for DE and FR markets; copy confirmed.

  - Attach or link final, QA-approved files.

  - Tag the assigned Web Developer (WD) and the Channel Lead (CL) for visibility.

  - If there were any minor adjustments made during QA (e.g., resized logos, corrected colors), document them clearly so the WD understands the context.

  - Make sure all files are properly versioned (e.g., vFinal, v2, Approved) to avoid confusion with earlier drafts

  - Update the status of the Asset Extraction task from QA In-Progress to Complete

  - Check that the Build task is assigned to a Web Developer. If not, reach out CL to do the assignment

  - If a WD has already been assigned:

  - Tag them in comments and confirm asset readiness.

  - If a WD is not yet assigned:

  - Immediately flag this to the CL for assignment.

  - Provide the CL with all required context to ensure a smooth handoff.

  - Do not assume the WD will check asset readiness independently. The GD-QA must confirm that ownership of the next step is clearly established.

- Build

Managed by: Web Developer (WD)
Oversight: Channel Lead (CL)

The Build stage is where approved assets are transformed into final deliverables. It relies heavily on the accuracy and completeness of the Asset Extraction phase and directly impacts the Quality Control stage.

  - When Build starts, i.e. the Developer picks the Build Task, WD will

  - Update Build task status from New ➝ In-Progress

  - This signals the start of development work.

  - Ensures visibility to the PC, CL, and QA team.

  - Always update status before starting work to avoid duplicate or conflicting assignments.

  - Update Project Status from Awaiting Execution ➝ Execution In-Progress (happens automatically with automation)

  - If Asset Extraction was applicable, the project should already be in Execution In-Progress.

  - Confirm the Project Status matches the actual state to avoid confusion in dashboards.

  - If the status isn’t updated automatically, notify the PC immediately.

  - Complete the required development activity and update relevant files, output, and notes in Comments on the Build task

  - Deliverables may include HTML builds, banners, landing pages, emails, or other channel-specific executions.

  - Upload final outputs and any supporting files (e.g., source files, preview links).

  - Document build notes, especially for:

  - Deviations from the original brief.

  - Placeholder content used pending client approval.

  - Technical challenges encountered and resolved.

  - Tag the CL in comments if there are noteworthy risks or changes.

  - Handling Build Failure

Managed by: Web Developer (WD), with oversight from Project Coordinator (PC) and Channel Lead (CL)

Sometimes, during the Build stage, the WD may discover that critical inputs are missing or incorrect. These should be handled systematically to avoid wasted effort and delays.

WD Identifies Missing Inputs

- Examples:

  - Copy deck not attached or outdated.

  - Image files missing for certain banner sizes.

  - Market-specific translation not provided.

  - Brand guideline updates not included in intake.

WD Raises an Issue

- Create an Issue task with type Pending Clarification.

- Assign the Issue to the PC.

- Clearly describe what is missing in the Issue description and comments.

- Tag the PC and CL in the comment for visibility.

Update Project and Task Status

- If the blocker prevents Build from progressing, PC updates the Project Status ➝ Pending Clarification, and updates the Issue task status from New to In-Progress

- Add a note in the Project comments, e.g., “Build paused — awaiting DE translation copy from LEM.”

- PC reaches out to LEM for clarification (assigns the Issue task to LEM)

LEM Provides Clarification

- Once the LEM responds with the missing files or details:

  - PC assigns the Issue task to themselves for verification.

  - PC checks that the updated information is correct and complete.

Verification & Closure

- If all gaps are resolved:

  - PC updates the Issue status from In-Progress ➝ Closed.

  - Project Status moves back to Execution In-Progress.

  - WD resumes the Build task.

- If still incomplete:

  - PC documents remaining gaps in comments.

  - Re-assigns the Issue back to the LEM.

  - Project Status remains in Pending Clarification until resolved.

4.3	Best Practices for Build

- Always double-check GD-QA notes before starting the build to ensure no missed instructions.

- Save and upload files in both working and final formats (e.g., .PSD + .JPG for banners, .HTML + .ZIP for emails).

- Keep Workfront comments up to date — never rely solely on chat or email for build-specific details.

- Use preview/test links wherever possible to make QC reviews easier.

- Flag risks early (e.g., “Layout not rendering as expected on Safari — testing fixes.”).

  - When Build is Complete, WD will:

- Update the status of the Build task from In-Progress ➝ Complete

  - Confirms development work is finished and deliverables are ready for QC review.

  - If issues were resolved during Build (via Issue tasks), ensure that the fixed deliverables are part of the final upload before marking Build Complete.

  - Add a final comment summarizing build notes, such as:

    - Number of deliverables completed.

    - Any deviations from original requirements.

    - Reference links for preview/testing.

  - Attach final build files (or provide access links).

- Assign the QA Audit Task to QA Lead

  - The QA Lead manages assignment to a QC resource.

  - Ensure the QA Audit task includes:

    - Reference to build notes.

    - Links to assets or preview builds.

    - Any specific instructions (e.g., “Check responsive behavior on iOS devices”).

  - Tag the QA Lead in the comments to ensure visibility and quick pick-up.

- Update the Project Status from Execution In-Progress ➝ In-QC (happens automatically with automation)

  - This transition signals that the project is officially moving into the QC phase.

  - Add a comment in Project-level notes, e.g.,

    - “Build completed on DD/MM. Assets uploaded and QA Audit task assigned to QA Lead.”

  - Verify that the status update reflects on all Workfront dashboards to keep stakeholders informed.

- QA Audit

Managed by: QA Lead
Oversight: Channel Lead (CL)

The QA Lead ensures that the project’s deliverables are properly prepared for a thorough review by the QC resource. Their role acts as a bridge between the Build and QC stages, confirming that the handoff from WD is complete and setting up the QC team for success.

  - When the QA Lead picks the QA Audit task, they will:

  - Perform a high-level review of the Notes, Comments, and attachments from the WD

  - Verify that all build deliverables are attached or linked.

  - Review WD’s comments for clarity, including:

    - Number and type of deliverables.

    - Any deviations from the original brief.

    - Any placeholders or pending dependencies.

  - Confirm files are accessible and not corrupted.

  - Do not assign the task to QC until all expected files and notes are verified.

  - Assign the QA Audit task to a QC resource

  - Choose a QC resource based on workload, specialization (e.g., banners, landing pages), and availability.

  - Add a quick assignment comment (e.g., “Assigning to [Name] for full QC review — assets confirmed complete.”).

  - If the task involves multiple deliverables, clearly specify which QC resource should handle which items (if split).

- Update the QA Audit task status from New ➝ Assigned to QA

  - This indicates that the QC resource is now responsible for the task.

  - Double-check that the Project Status is updated to In-QC (if WD hasn’t already done so).

  - Add a final note tagging the QC resource to notify them of the assignment.

5.2	When the QC Resource picks the QA Audit task, they will:

- Update the status of the QA Audit task from Assigned to QA ➝ QA In-Progress

  - This indicates the formal start of the QC process.

  - Ensures visibility for PC, CL, and QA Lead on task progress.

  - Optionally, Add a short comment such as: “QC review started on DD/MM.”

    - Perform review of the deliverables, matching them with initial requirements, using Brand Guidelines, QC Checklist, and best practices

    - Confirm formats, sizes, and versions match the intake form.

    - Validate deadlines and ensure files are delivered as per scope.

    - Verify use of approved logos, fonts, and colors.

    - Ensure layouts adhere to brand standards.

    - Confirm copy matches the approved text from LEM/Submitter.

    - Check localized content for language accuracy and cultural relevance.

    - Confirm links, animations, or interactive elements function correctly.

    - Ensure responsive behavior across specified devices/platforms (if applicable).

    - Follow the channel-specific QC Checklist thoroughly to avoid oversight.

    - Add clear, structured notes in the QA Audit task comments.

  - Best Practices for QC Resources

    - Always use the QC Checklist — never rely on memory, even for simple deliverables.

    - Be clear and specific in findings — avoid vague notes like “banner incorrect.”

    - Group feedback logically (by deliverable or issue type) to make it easier for WD/GD to fix.

    - Tag PC and CL for critical issues that may impact project timelines.

    - Maintain objectivity — base findings on documented guidelines and requirements, not personal preferences.

    - Use severity levels (Critical, Major, Minor) to help prioritize fixes.

5.4	When QC FAILS, QC Resource will:

  - Add relevant notes, findings, issue details in the comments of the QA Audit task, and also in the Bug Fixing task (or use referencing statements in the tasks to avoid duplication)

  - Capture all findings clearly and precisely.

  - Attach screenshots, files, or references to help Designers/Developers address issues quickly.

  - Use referencing if the same details apply to both tasks (e.g., “See Bug Fixing task for full details on issue list”)

  - Tag the assigned resource and CL for visibility.

    - Update the QA Audit task status from QA In-Progress ➝ Complete

- Assign the Bug Fixing task to Designer/Developer (based on QC findings), who initially worked on the Extraction/Build task

  - If the issue is related to Asset Extraction, assign it to the GD who handled it (refer to Section 3).

  - If the issue is related to Build, assign to the WD who developed it (refer to Section 4).

  - If the original resource is unavailable, consult with CL to reassign and manage workload.

5.5	Managing Bug Fixing Task

Important: 
- All bugs are resolved within the Bug Fixing task.
- Project Status will remain unchanged until all bugs are fixed and QC passes.

- Designer/Developer updates Bug Fixing task status

  - From New ➝ In-Progress when they start working on fixes.

  - After completing fixes, update from In-Progress ➝ Assigned to QA, assigning it to a QC resource (preferably same QA resource who complete the QA Audit Task) OR the QA Lead (if QC resource is unavailable)

- QC Resource updates Bug Fixing task status

  - From Assigned to QA ➝ QA In-Progress when starting their review.

  - After reviewing:

    - If PASS: Update Bug Fixing Task to Complete.

        - Add relevant notes, findings, in the comments of the Bug Fixing task

        - Provide a summary of fixes validated in the DPM review task

        - Ensure PC has access to all final deliverables and bug fix notes

        - Tag PC in comments for visibility.

    - If FAIL: Add new findings in comments and restart the cycle by reassigning to GD/WD, and update Status back to New

- Cycle Continuation

  - The Bug Fixing cycle may repeat as needed.

  - There is no limit on the number of bugs documented.

  - All Designers/Developers/QC Leads/QC Resources collaborate in the same Bug Fixing task until PASS

  - When QC PASSES, the QC Resource will:

- Document Findings in the QA Audit Task Comments

    - Add a summary confirming all deliverables meet the requirements.

    - Clearly state that QC has passed. (e.g. “QC Pass: All 5 EN banners and 2 FR banners verified. Dimensions, copy, and brand guidelines confirmed.”

    - If minor non-blocking notes exist (e.g., optional improvements), mention them for awareness but do not hold up the process.

- Update the QA Audit Task Status from QA In-Progress ➝ Complete

- Assign the DPM Review Task to PC

- Update the DPM Review Task status from ➝ In-Progress

- Update the Project Status from In-QC ➝ Pending Review

6.	DPM Review

Managed by: Project Coordinator (PC)
Oversight: Channel Lead (CL), with context from QC Resource

The DPM Review acts as a final internal checkpoint before EL and/or Affiliate review or client-facing submission. It ensures that all project expectations, brand standards, and business context have been met.

6.1	When PC starts the Project Review, PC will

- Review the Deliverables, Compare them with the requirements and brand guidelines

  - Requirement Verification

    - Cross-check the final deliverables against:

      - Intake form

      - Original brief

      - Any clarification notes exchanged during the process

    - Ensure all listed deliverables (e.g., banner sizes, languages, formats) are present and named correctly.

  - Brand Guidelines Compliance

    - Confirm that designs, layouts, messaging, and CTAs align with current brand guidelines.

    - Check usage of logos, fonts, colors, spacing, etc.

    - Refer to brand guideline documents or links attached in the initial intake.

  - QC Findings Re-check

    - Review the QC resource summary to ensure all prior issues were addressed.

## 6.2	Best Practices for DPM Review

- Review both at the file and comment level — important context is often shared in the notes.

- Ensure naming consistency and formatting of all deliverables for ease of client handoff.

- Compare against the full intake, not just the final QC summary — sometimes early requirements get lost downstream.

- Keep communication in Workfront to ensure traceability.

6.3	When PC review is PASS, PC will:

- Add relevant notes, information, and references as Comment in the EL Review task

  - Include:

    - Confirmation that deliverables match the intake and brief.

    - A list of deliverables reviewed.

    - References to key QC findings already resolved.

    - Any special instructions or considerations

- Update the DPM Review task from In-Progress ➝ Complete

- Tag & Assign the EL Review task to LEM/Requester

- Update the EL Review task status from New ➝ In-Progress (SLA Ends HERE)

- Update the Project Status from Pending Review ➝ In-Review (happens automatically with automation)

Project Ageing Control & Closure Protocol

To maintain accurate project lifecycle management and reporting hygiene, ageing-based closure control is applied at the DPM Review stage.

- Project ageing is calculated in calendar days from the date the project was sent for review.

- At 45 days of ageing, PCs must initiate a follow-up with the respective LEM/market to confirm status and identify any pending dependencies.

- Projects reaching 60 calendar days of ageing must be moved toward closure.

Closure Action (60+ Days):

- Inform the LEM/market referencing the 14 Jan 2026 communication.

- Closure should proceed unless there is an active, justified dependency.

- Any exception to closure must be clearly documented in Workfront with reason.

Purpose:
Ensures clean project lifecycle governance, prevents dormant projects, and maintains accurate SLA and reporting data.

Guidance for PCs

- Monitor project ageing regularly via dashboards. (Workfront – Hogarth – Projects In review ageing > 45 days)

- Start communication at 45 days — do not wait until 60.

- Use standardized communication while reaching out.

- If no response is received for 60+ day projects, proceed with closure.

- Record all communication and any exception notes in Workfront.

- Escalate only if dependency impacts other active work.

Email to Requesters

Day 45:
Subject: Project Status Check – Ageing Review

Hi [Name],

As part of our regular project lifecycle review, we noticed this project has now reached 45 calendar days since it was sent for review.

We just wanted to check if there are any pending actions, updates, or dependencies from your side that we should be aware of. This will help us ensure the project progresses smoothly and remains aligned with expectations.

Please share any updates at your convenience. We’ll continue to monitor the project status and will follow up as needed.

Thank you.

Day 60:
Subject: Project Status Confirmation

Hi [Name],

We are reviewing projects that have been open for an extended duration. This project has now crossed 60 calendar days from the date it was sent for review.

In line with project lifecycle governance and the communication dated 14 Jan 2026, we will proceed with closure unless there is an active dependency or pending action from your side.

Please let us know if the project needs to remain open; otherwise, we will move ahead with closure.

Thank you.

Workfront Comment Boilerplate

Project Ageing Review:
This project has exceeded 60 calendar days from the date sent for review. As per closure governance and the communication dated 14 Jan 2026, closure is being processed.

LEM/market notified

----

We understand that in many instances, obtaining the Veeva code can be challenging despite your best efforts. This has sometimes prevented DPMs from closing tickets, which impacts our overall performance data.

As a consequence, the auto-closure procedure is updated as follows:

- All projects sent for review (SFR) that are inactive for more than 60 days will be closed, even if a Veeva number is not available. This is applicable across all channels.

- Despite this change, please remember that ensuring Veeva numbers are shared during project initiation is still essential. The LEM team is encouraged to obtain the Veeva number from affiliates at the start of each project.

If a Veeva number isn't available during the project logging phase, please make every effort to provide it before the first draft is delivered.
-----

6.4	When PC review is FAIL, PC will:

- Create an Issue, with Issue Type as “WD Miss”

- Add relevant notes, information, and references as Comments in the created Issue

  - Detail exactly what failed and why.

- Assign the Issue to the Designer/Developer, as the case may be

  - If the issue is related to Asset Extraction, assign it to the GD (refer to Section 3.1).

  - If the issue is related to Build, assign it to the WD (refer to Section 4).

  - If PC prefers, they may assign the Issue to the relevant Channel Lead (CL), who can then re-assign based on capacity.

6.5	Managing Issue Task

Important: 
- All Issues will be resolved within the Issue task.
- Project Status and other task statuses remain unchanged until all issues are fixed and re-verified.

- Designer/Developer

  - Updates Issue task status from New ➝ In-Progress when starting fixes.

  - Once fixes are complete, updates from In-Progress ➝ Assigned to QA, tagging QA Lead or QC Resource.

- QA Resource

  - Updates Issue task status from Assigned to QA ➝ QA In-Progress when review starts.

  - Reviews fixes against Issue notes.

  - If PASS: Updates Issue task to Complete.

        - Add relevant notes, findings, in the comments of the Issue task

        - Provide a summary of fixes validated in the issue task

        - Ensure GD/WD has access to all final deliverables and Issue fix notes

        - Tag GD/WD in comments for visibility.

  - If FAIL: Documents new findings in comments and restarts cycle by re-assigning back to GD/WD, and update status back to New

- Cycle Continuation

  - This loop repeats until the Issue is resolved and passes QA.

  - There is no limit to the number of issues created or cycles run.

  - All involved parties (GD, WD, QA, CL) collaborate in the same Issue task for full traceability.

7	Engagement Lead & Affiliate Review

Managed by: Engagement Lead (EL), Affiliate, and Project Coordinator (PC)

Oversight: Project Coordinator (PC)

Once the Project is into the EL Review or the Affiliate Review Status, PC will

- Monitor Completion of EL and Affiliate Review

- Ensure both EL and Affiliate Review tasks show 100% Complete in Workfront.

- Cross-check comments for any final observations or optional feedback.

- If reviews are marked complete but comments suggest pending clarifications, confirm with LEM before moving forward.

- LEM Can raise an issue task (and assign the same to PC) for

  - Quality Miss

  - Change Round

PC, CL, Developer and Designer to work on the Issue task, by updating status and assignees, and finally PC will send the deliverables to LEM for review again.

While the Issue (CR), is being worked upon, please set the project and task status accordingly and make sure the comments are updated:

    - PC to review the Issue CR/QM, and assign the same to CL. PC to update required fields in Workfront and set the Issue status from New to “Assigned to Execution” and Project status as “CR in Execution” (happens automatically with automation)

    - PC to update the Issue Task Name as:

      - CR1 - << Free Text >>

      - CR2 - << Free Text >>, and so on…

      - QM1 - << Free Text >>

      - QM2 - << Free Text >>

    - PC to mandatorily populate the fields below, with suitable option

      - LEM Feedback

      - Affiliate feedback

    - CL to review the issue CR/QM:

      - For any clarifications, Update the Issue Task status from “Assigned to Execution” to “Pending Clarification” AND Project Status from “CR In Execution” to “Pending Clarification”.

      - If the ask/s are clear to proceed,

        - CL to update the CR Acceptance Date,  CR Expected Delivery Date AND Planned Completion Date.

        - CL to assign the issue task to Developer/Designer

    - Developer/Designer to update the Issue Task status from “Assigned to Execution” to “Execution In-Progress”,

    - Post Development, Designer/Developer to update the Issue task status from “Execution In-Progress” to “Assigned to QA” and assign the issue task to QA Lead

    - QA Lead to review and assign the issue task to QA resource

    - QA Resource to update the issue task status from “Assigned to QA” to “QA In-Progress”, and complete the QC of the issue task

      - If the QC check fails, QC resource will update the status of the issue task to “Rework identified” and assign it back to the developer/designer. (Tag Channel Lead as well)

      - Designer/Developer to update the issue task status from Rework identified to In-Progress, and gets the development completed for the change request.

      - Follow the process from bullet 4.

      - Once QC is Complete, QA resource will assign the Issue Task back to PC and update the Issue Task status from “QA In-progress” to “QA Completed”.

      - QA Resource to assign the Issue Task to PC and Update the Issue Task Status from “QA Completed” to “Execution Complete”

      - QC resource to update the projects status as “CR pending Review” (happens automatically with automation)

      - PC to review and deliver the Issue Task to LEM, i.e. Update the Issue status from “Execution Complete” to “Closed”

      - PC to update the Project status from “CR Pending Review” to “CR In Review”

      - PC to populate the CR Sent for Review Date

- If the EL Review and Affiliate Review are at 100% Complete, and the “Client Approval Received” task is not started:

- PC will assign the “Client Approval Needed” task to himself.

- If the “Client Approval Task” is already assigned to PC by the LEM/Affiliate:

- PC will proceed with the Final Asset Upload on Veeva.

- The upload may be optional — dependent on placeholder or final details provided by the requester.

- Document the upload link/reference in Workfront comments.

- Once the Veeva Upload is Complete:

- PC will inform the LEM/Affiliate with a Workfront comment.

- Mark the Project as Complete in Workfront.

Project Closure for Long-Running Projects (90+ Days)

Purpose

To ensure Workfront data hygiene, accurate reporting, and audit readiness by systematically managing projects that remain open for an extended duration without activity.

Definition

A project is considered long-running if it remains open for 90 calendar days from the Project Start Date, defined as the date when the Asset Audit task was moved to “In Progress.”

Guidance for Project Coordinators (PCs)

- PCs must regularly monitor projects that cross the 90-day open threshold.

- Once a project reaches 90 days:

  - PCs should inform the LEM via email that the project is being considered for closure.

  - PCs may manually close the project in Workfront without waiting for explicit confirmation.

This is a guidance-based process, not a rigid rule.

Exception Handling

- Exceptions may apply in cases such as:

  - Known future activation

  - Market or affiliate dependency

  - Strategic or business hold

- Any agreed exception must be:

  - Aligned with the LEM

  - Clearly documented in Workfront, including:

    - Reason for keeping the project open

    - Confirmation or alignment details

Automation Support

- An automated notification email is being implemented for the PC layer.

- This email will be sent every Tuesday and Friday morning, listing:

  - Projects that have crossed the 90-day open condition

- PCs should:

  - Use this list to communicate with the LEM early in the day

  - Allow time for response or exception requests

  - Proceed with project closure by EOD if no response is received

Documentation Requirements in Workfront

For transparency and audit purposes:

- Closure decisions must be reflected in:

  - Project status updates

  - Workfront comments or notes

- Exceptions must include:

  - Clear reason for exception

  - Stakeholder alignment details

Governance Notes

- This process helps prevent inactive or stale projects from impacting:

  - SLA reporting

  - Operational dashboards

  - Audit outcomes

- Accurate and timely closure is a shared responsibility across roles.